## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
| Finishing up coworking space screen, checking that the profile is functional, working on the screen's appearance and authenticating routes. |  | Norhan & Mariam | Yasmin | Shaza
| Working on Member screen, checking that the profile is functional, working on the screen's appearance and authenticating routes. |  | Shaza & Mariam | Norhan | Yasmin
| Finishing up cosultancy agency screen, checking that the profile is functional, working on the screen's appearance and authenticating routes. |  | Malak & Abdelrahman | Janna | Eman
| Finishing up admin screen, checking that the profile is functional, working on the screen's appearance and authenticating routes. |  | Reem & Lina | Yasmin | Mariam
| Finishing up partner screen, checking that the profile is functional, working on the screen's appearance and authenticating routes. |  | Janna & Eman | Lina | Reem
| Creating and editing posts for users. |  | Yasmin | Mariam | Malak
| Connecting chatting application with front end for users to be able to chat together. |  | Yasmin | Mariam | Malak
| Working on the landing page of the website. |  | Yasmin | Abdelrahman | Reem
| Working on notification front end and back end. |  | Lina | Janna | Eman
| Viewing all user types profiles from another profile screen |  | Norhan | Shaza | Abdelrahman
| Authentication code. |  | Yasmin | Lina | Norhan
| Authenticating routes and linking code. |  | all Team Members
| Updates to member back end related APIs. |  | Shaza | Mariam | Yasmin