## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.2 | As a registered user I can search for coworking spaces based on location and capacity, so that I can choose which one suits me the best. | 3 | Malak | Mariam | Nour
1.6 | As a registered user I can receive a notification confirming my coworking space room booking, so that I can learn about the confirmation of my booking. | 5 | Malak | Mariam | Nour
1.8 | As a registered user I can edit a coworking space room booking to request a larger room if available, so that I can adjust to attendees’ number changes. | 3 | Reem | Mariam | Nour
1.11 | As a registered user I can view suggestions of coworking spaces when creating an event (or workshop or course) depending on the location and capacity and time of the event, so that it would be easier for my to find a suitable location easily. | 5 | Reem | Mariam | Nour
3.5 | As an Admin, I want to negotiate with partners so that any missing information is supplied and any unclear information is clarified. | 3 | Nourhan | Yasmin | shaza
4.3 | As a Partner, I want to negotiate with the admin, so that I’m able to clarify my requirements. | 3 | Yasmin | Nourhan | Shaza
4.4 | As a Partner, I want to edit my task description so that any missing information is supplied or any unclear information is clarified. | 2 | Janna | Lina | Eman
4.5 | As a Partner, I want to view the state of my task’s life cycle, so that I can keep track of how far the execution of my task is. | 2 | Lina | Janna | Eman
4.6 | As a Partner, I want to review finished tasks, so that I can give feedback and rate the member who was assigned to my task. | 2 | Eman | Janna | Lina
4.7 | As a Partner, I should be able to choose a consultancy agency, so that they help me complete my task description. | 3 | Lina & Eman & Janna | janna | eman
5.2 | As a consultancy agency, I could filter tasks posted by partners, so that I can give job recommendations for members. | 5 | Mariam | Reem | Yasmin
5.5 | As a consultancy agency, I can supply managerial roles, so that workflow is more organized. | 3 | Yasmin | Nourhan | shaza
5.4 | As a consultancy agency, I can negotiate with admins, so that I am sure that the task description is fair and clear to all entities. | 3 | Shaza | Yasmin | Nourhan
5.6 | As a consultancy agency, I can apply for tasks, so that I can find freelancers willing to be assigned for working on this task. | 5 | Shaza & Nourhan | Nourhan | Shaza
MONGO DB Additions
1 | As a Partner, I want to submit a task description to be posted, so that members can apply for my task. | 2 | Eman Essam | Lina | Janna
1.1 | As an Admin, I want to check a task description submitted by a partner, so that I could check the validity of the information submitted in the description. | 2 | Janna Elghabaty | Lina | Eman
1.2 | As an Admin, I want to post tasks on the application, so that members can apply for them. | 5 | Lina Shawky | Janna | Eman
1.3 | As a Member, I want to apply for tasks based on my skills, experience level and certificates, so that I can be assigned to one of the tasks available. | 5 | Eman Essam | Lina | Janna
1.4 | As an Admin, I want to view and assign the most suitable member of those who applied to the task so that the task would be handled by someone. | 2 | Lina Shawky | Janna | Eman
1.6 | As an Admin, I want to activate accounts after signing contracts and agreements, so that users can access the application. | 5 | Janna Elghabaty | Lina | Eman
1.7 | As an Admin, I could view users profile updates/changes so that data is kept consistent and valid | 2 | Reem Khaled | Mariam | Nour
1.8 | . As an Admin, I could accept or reject users profile updates/changes so that data is kept consistent and valid | 5 | Reem Khaled | Mariam | Nour
1.9 | As a partner coworking space, I can CRUD my rooms, so that users can remain updated with the rooms that they can book. | 8 | Mariam | Yasmin | Nourhan
2 | As a partner coworking space, I can CRUD my rooms’ schedule, so that I can reflect any room changes on the schedule. | 8 | Mariam | Malak | Reem
2.1 | As a registered user I can view all coworking spaces partnered with Lirten hub, so that I can learn about suitable coworking spaces for me or my clients. | 3 | Shaza | Nourhan | Yasmin
2.2 | As a registered user I can view coworking spaces' profiles, so that I can view their details and learn needed information about them. | 5 | Shaza | Nourhan | Yasmin
2.3 | As a registered user I can view schedules of coworking spaces rooms, so that I can reserve a room at the time that suits me the best. | 2 | Nourhan | Shaza | Yasmin
2.4 | As a registered user I can only book available rooms of coworking spaces, so that my booking does not overlap with another user’s booking. | 5 | Nourhan | Shaza | Yasmin
2.5 | As a registered user I can view my confirmed bookings, so that I’m able to learn about all my confirmed bookings and manage them. | 1 | Yasmin | Shaza | Nourhan
2.6 | As a registered user I can cancel a coworking space room booking within a specified time, so that I can accommodate to any sudden changes to my plan. | 5 | Yasmin&Nourhan | Shaza | Nourhan
2.7 | As a registered user I can CRUD an event/workshop/course, so that I can manage my events freely. | 8 | Abdelrahman & Malak | Mariam | Reem
2.8 | As an unregistered user, I can view the home page but can't access anything unless I create an account and the account is verified, so that data is protected and only accessed by verified users and new users are allowed to join the network in an organised and well planned manner. | 2 | Abdelrahman & Malak | Mariam | Reeem
2.9 | As a registered user, I can add, update and delete my information so that my profile is having my latest information that I want it to appear on it. | 3 | Abdelrahman & Malak | Mariam | Reem
3 | As an unregistered user, I can create an account so that I can use the application's facilities | 5 | Yasmin | Nourhan | Shaza