## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As a Partner, I want to submit a task description to be posted, so that members can apply for my task. | 2 | Janna Elghabaty
1.1 | As an Admin, I want to check a task description submitted by a partner, so that I could check the validity of the information submitted in the description. | 2 | Janna Elghabaty | 1
1.2 | As an Admin, I want to post tasks on the application, so that members can apply for them. | 5 | Lina Shawky | 1,1.1
1.3 | As a Member, I want to apply for tasks based on my skills, experience level and certificates, so that I can be assigned to one of the tasks available. | 5 | Eman Essam | 1,1.1,1.2
1.4 | As an Admin, I want to view and assign the most suitable member of those who applied to the task so that the task would be handled by someone. | 2 | Lina Shawky | 1,1.1,1.2,1.3
1.5 | As a Member, I want to receive acceptance/ rejection for tasks I applied for, so that I can receive a task orientation invitation in case of acceptance or apply for another task in case of rejection. | 2 | Eman Essam | 1,1.1,1.2,1.3,1.4
1.6 | As an Admin, I want to activate accounts after signing contracts and agreements, so that users can access the application. | 5 | Janna Elghabaty
1.7 | As an Admin, I could view users profile updates/changes so that data is kept consistent and valid | 2 | Reem Khaled
1.8 | . As an Admin, I could accept or reject users profile updates/changes so that data is kept consistent and valid | 5 | Reem Khaled | 1.7
1.9 | As a partner coworking space, I can CRUD my rooms, so that users can remain updated with the rooms that they can book. | 8 | Lina,Eman,Mariam
2 | As a partner coworking space, I can edit and view my rooms’ schedule, so that I can reflect any room changes on the schedule. | 6 | Mariam Heikal | 1.9
2.1 | As a registered user I can view all coworking spaces partnered with Lirten hub, so that I can learn about suitable coworking spaces for me or my clients. | 3 | Shaza | 1.9,2
2.2 | As a registered user I can view coworking spaces' profiles, so that I can view their details and learn needed information about them. | 5 | Shaza | 1.9,2,2.1
2.3 | As a registered user I can view schedules of coworking spaces rooms, so that I can reserve a room at the time that suits me the best. | 3 | Nourhan | 1.9,2,2.1
2.4 | As a registered user I can only book available rooms of coworking spaces, so that my booking does not overlap with another user’s booking. | 5 | Nourhan | 1.9,2,2.1,2.3
2.5 | As a registered user I can view my confirmed bookings, so that I’m able to learn about all my confirmed bookings and manage them. | 3 | Yasmin | 1.9,2,2.1,2.3
2.6 | As a registered user I can cancel a coworking space room booking within a specified time, so that I can accommodate to any sudden changes to my plan. | 5 | Yasmin | 1.9,2,2.1,2.3
2.7 | As a registered user I can CRUD an event/workshop/course, so that I can manage my events freely. | 8 | Abdelrahman & Malak
2.8 | As an unregistered user, I can view the home page but can't access anything unless I create an account and the account is verified, so that data is protected and only accessed by verified users and new users are allowed to join the network in an organised and well planned manner. | 2 | Abdelrahman & Malak
2.9 | Registered User , add, update , delete, my information | 3 | Abdelrahman & Malak